Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 15-07-2026 |
| --- | --- |
| Team ID |  |
| Project Name | ShopEZ – Full Stack MERN E-Commerce Platform |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story No. | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration | USN-1 | As a customer, I can register using my email and password. | 3 | High | Team |
| Sprint-1 | Login | USN-2 | As a customer, I can log in securely using JWT authentication. | 2 | High | Team |
| Sprint-1 | Profile | USN-3 | As a customer, I can view and update my profile information. | 2 | Medium | Team |
| Sprint-1 | Admin Login | USN-4 | As an admin, I can log in to access the admin dashboard. | 2 | High | Team |
| Sprint-2 | Product Catalog | USN-5 | As a customer, I can browse all available products. | 3 | High | Team |
| Sprint-2 | Product Search | USN-6 | As a customer, I can search products by name. | 2 | High | Team |
| Sprint-2 | Product Filter | USN-7 | As a customer, I can filter products by category and price. | 2 | Medium | Team |
| Sprint-2 | Product Details | USN-8 | As a customer, I can view complete product details. | 2 | High | Team |
| Sprint-3 | Shopping Cart | USN-9 | As a customer, I can add, update and remove products from my cart. | 5 | High | Team |
| Sprint-3 | Wishlist | USN-10 | As a customer, I can save products to my wishlist. | 2 | Medium | Team |
| Sprint-3 | Checkout | USN-11 | As a customer, I can place an order with shipping details. | 5 | High | Team |
| Sprint-3 | Payment | USN-12 | As a customer, I can complete payment using Razorpay or Cash on Delivery. | 3 | High | Team |
| Sprint-4 | Order Management | USN-13 | As a customer, I can view my order history and track orders. | 3 | High | Team |
| Sprint-4 | Product Management | USN-14 | As an admin, I can add, edit and delete products. | 5 | High | Team |
| Sprint-4 | Category Management | USN-15 | As an admin, I can manage product categories. | 3 | High | Team |
| Sprint-4 | Banner Management | USN-16 | As an admin, I can upload and manage homepage banners. | 2 | Medium | Team |
| Sprint-4 | User Management | USN-17 | As an admin, I can view and manage registered users. | 3 | Medium | Team |
| Sprint-4 | Order Management | USN-18 | As an admin, I can update order status and manage orders. | 4 | High | Team |
| Sprint-4 | Dashboard Analytics | USN-19 | As an admin, I can view sales, users and revenue analytics. | 3 | Medium | Team |
| Sprint-4 | Coupon Management | USN-20 | As an admin, I can create and manage discount coupons. | 2 | Low | Team |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 9 | 7 Days | 15-06-2026 | 21-06-2026 | 9 | 21-06-2026 |
| Sprint-2 | 9 | 7 Days | 22-06-2026. | 28-06-2026 | 9 | 28-06-2026 |
| Sprint-3 | 15 | 7 Days | 29-06-2026 | 04-07-2026 | 15 | 04-07-2026 |
| Sprint-4 | 22 | 10 Days | 05-07-2026 | 14-07-2026 | 22 | 14-07-2026 |

Velocity:

Imagine we have a 10-day sprint duration, and the velocity of the team is 20 (points per sprint). Let’s calculate the team’s average velocity (AV) per iteration unit (story points per day)

Sprint; Story Points Completed; Duration (Days); Velocity (Story Points/Day). Sprint-1; 9; 7; 1.29. Sprint-2; 9; 7; 1.29. Sprint-3; 15; 7; 2.14. Sprint-4; 22; 10; 2.20. Average Velocity; 55; 31; 1.77 Story Points/Day.

Burndown Chart:

A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts